Date:	6th February 2017
Time:	13:00 – 14:00
Place:	Atrium Building

Attendees: D Fryer, V Dia, M Smuts

The meeting was held to check the schedule for students signed up for the pilot and discuss the timing of the sessions.

There was a discussion about the length of time each session would take. Whilst it is possible they will be completed in just over an hour, we will need to schedule 2 hours for each. This is because some students will take longer to complete sections of the game and some may need more breaks.

The process will be:
- First Questionnaire
- Safety brief and introduction
- Game tutorial
- 5 minute break
- Game level 1-3
- 5 minute break
- Game level 4-6
- 5 minute break
- Second Questionnaire

David pointed out that the students were not allowed to “have another go” once the game was complete, as this would invalidate the pilot.

The schedule allows for 3 students per session and 3 sessions per week, starting on Monday 20th February:
Monday 14:00 – 16:00
Wednesday 14:00 16:00
Friday 15:00 17:00

Both MS and VD volunteered to be there for these sessions. The plan is to Set up the games machines on the Monday morning.

MS to request headphones if they are available. If not MS to make alternative arrangements.

The game is currently undergoing testing and bug fixes.
DF requested that the 3rd level text be changed to say “area responsible for “ and check the terms “Wernicke” “Somatasensory” “Brocca's”. The term Association area is possibly misleading MS to check.

MS to include Alison Taylor (tech support for the Psychology department) in communications regarding the pilot and the use of A1.17.

Time line:
Final user tests on Thursday 16th at 16:00 in A2.12
Completion date 17th February 2017
First student usage planned for 20th February 2017
Estimated pilot running time 3 weeks in room A1.17

Errors and Omissions – please let me know